## TASK
task_code | task_name | start_date | end_date
Activity ID | Activity Name | (*)Start | (*)Finish
A01 | Mobilization to site | 23-Feb-26 | 29-Apr-26
A02 | Obtaining an Approval | 02-Feb-26 | 23-Feb-26
B01 | Demolition of Existing RCC Wall - Wall Between Laundry Room & DB room | 23-Feb-26 | 26-Feb-26
B02 | Removal of Existing Window, Enlarging the opening - Kitchen Area | 27-Feb-26 | 02-Mar-26
B03 | Removal of Non-Structural Pillar and existing window - Kitchen Island Area | 26-Feb-26 | 28-Feb-26
B04 | Demolition of Existing RCC wall and Glass Door - GF Living Area | 26-Feb-26 | 03-Mar-26
B05 | Removal of Existing Fixed Window - GF Living Area | 02-Mar-26 | 03-Mar-26
B06 | Removal of Existing Fixed Window - FF Hallway Area | 02-Mar-26 | 03-Mar-26
B07 | Removal of Existing RCC wall to create new door opening - In Between of GF Living Area to External Area | 02-Mar-26 | 06-Mar-26
B08 | Removal of Non-Structural wall to create a new door opening, glass window & Enlarged window opening - Master Bedroom | 04-Mar-26 | 07-Mar-26
B09 | Removal of Non-Strucutural wall near existing door - Near Door in Master Bedroom | 06-Mar-26 | 07-Mar-26
B10 | Demolition of Existing wall to create a window opening - Master Bedroom Dressing Area | 05-Mar-26 | 07-Mar-26
B11 | Demolition of Non-Structural wall and Modification of Existing Door Opening - FF Suite Joud Bedroom Area | 05-Mar-26 | 07-Mar-26
B12 | Demolition of Existing RCC wall to create a Window Opening - GF Suite Invitee | 05-Mar-26 | 11-Mar-26
C01 | Supply and Construction of Blockwork to close existing window opening - GF Suite Invitee | 12-Mar-26 | 16-Mar-26
C02 | Supply and Installation of new walls - Side of Staircase Area | 17-Mar-26 | 21-Mar-26
C03 | Supply and Installation of new walls - GF Dining Area & Hallway Area | 21-Mar-26 | 25-Mar-26
C04 | Supply and Installation of new walls - Front of Staircase Area | 17-Mar-26 | 21-Mar-26
C05 | Modification of Existing Bulkhead Ceiling to replace curved corners w/ right-angled corners - Salon & Salle A Manger | 18-Mar-26 | 02-Apr-26
C06 | Modification of Existing Bulkhead Ceiling to create a flat ceiling - Master Bedroom | 12-Mar-26 | 17-Mar-26
C07 | Supply and Installation of LVT flooring in chevron pattern, 3mm thickness with self-leveling - Salle De Sport | 09-Apr-26 | 15-Apr-26
C09 | Supply and Application of Interior Paint on demolished affected walls and newly constructed walls | 08-Apr-26 | 16-Apr-26
C10 | Surface Preparation, Pressure washing, crack repair, & App. of 2 coats of Exterior Paint on demolished and new walls | 30-Mar-26 | 04-Apr-26
C11 | Supply, Cutting to size, & Intallation of Travertine Marble on staircase front - Front of staircase & hall D'entree | 23-Mar-26 | 28-Mar-26
C12 | Supply & Installation of Double - sided gypsum board partition - Master Bedroom | 18-Mar-26 | 24-Mar-26
C13 | Supply & Installation of Gypsum Board Bulkhead - Salle de Sport | 01-Apr-26 | 03-Apr-26
C14 | Cutting & Preparation of Openings for trimless AC Grille in Gypsum Board ceiling/wall - Salle de Sport | 06-Apr-26 | 06-Apr-26
C15 | Supply and Installation of stone-look sheet cladding - Patio D' Entree | 20-Apr-26 | 12-May-26
C16 | Supply, Fabrication & Installation of customized CNC-cut aluminum structure - Patio D' Entree | 01-Apr-26 | 18-Apr-26
C17 | Supply, Fabrication & Installation of motorized aluminum gate - Main Gate | 13-Mar-26 | 31-Mar-26
D01 | Installation only of electrical sockets, switches, speaker provision, data provision, lights, cable pulling, wall chasin | 09-Apr-26 | 19-May-26
E01 | Supply, fabrication & installation of black matt aluminum patio door system - Master Bedroom (Patio Door) | 13-Mar-26 | 16-Mar-26
E02 | Supply, fabrication & installation of Sliding aluminum window - Sejour Enfant | 13-Mar-26 | 16-Mar-26
E03 | Supply, fabrication & installation of Fixed aluminum-framed glass window - Salon | 13-Mar-26 | 16-Mar-26
E04 | Supply, fabrication & installation of black matt aluminum patio door system - Salon | 13-Mar-26 | 17-Mar-26
E05 | Supply, fabrication & installation of fixed aluminum-framed glass window - Salon | 13-Mar-26 | 14-Mar-26
E06 | Supply, fabrication & installation of sliding aluminum-framed glass window - Kitchen Area | 16-Mar-26 | 17-Mar-26
E07 | Supply, fabrication & installation of fixed aluminum-framed glass window - Chambre De Bonne | 17-Mar-26 | 18-Mar-26
E09 | Supply, fabrication & installation of hinged aluminum-framed glass window - Suite Invitee | 16-Mar-26 | 23-Mar-26
E10 | Supply, fabrication & installation of fixed aluminum-framed glass window - Salle de Sport | 07-Apr-26 | 09-Apr-26
E11 | Supply, fabrication & installation of fixed glass panel with hinged aluminum door - Salle de Sport | 07-Apr-26 | 11-Apr-26
E12 | Supply, fabrication & installation of double hinged glass door w/ wood leaf coated frame - Sejour & Salle A Manger | 21-Mar-26 | 26-Mar-26
E13 | Supply, fabrication & installation of single hinged glass door w/ aluminum frame - Salle de Sport | 07-Apr-26 | 09-Apr-26
E14 | Supply, fabrication & installation of black matt aluminum patio door system - Cuisine De Finition | 25-Mar-26 | 27-Mar-26
E15 | Supply, fabrication & installation of single hinged glass door w/ aluminum frame - Cabine de Massage | 10-Apr-26 | 11-Apr-26
E16 | Supply, fabrication & installation of black matt aluminum patio door system - Cabine de Massage | 10-Apr-26 | 13-Apr-26
E17 | Supply, fabrication & installation of glass panel & hinged/frameless door - Salle de Sport | 10-Apr-26 | 14-Apr-26
E18 | Supply, fabrication & installation of hinged aluminum-framed glass window - Master Bedroom & Suite Joud | 28-Mar-26 | 03-Apr-26
E19 | Supply, fabrication & installation of hinged aluminum-framed glass window - Master Bedroom Dressing Area | 28-Mar-26 | 30-Mar-26
E20 | Supply, fabrication & installation of fixed aluminum-framed glass window - Patio D'Entree | 28-Mar-26 | 31-Mar-26
F02 | Enclosed of Garage Area | 23-Feb-26 | 06-Apr-26
G01 | Removal of existing interlock and tiles surfaces | 23-Feb-26 | 07-Mar-26
G02 | Removal of existing plants & palm tree | 25-Feb-26 | 07-Mar-26
G03 | Supply and Installation of new outdoor tiles | 04-Mar-26 | 26-Mar-26
G04 | Swimming Pool Work | 25-Feb-26 | 12-Mar-26
G05 | Electrical Work Garden Area | 03-Mar-26 | 16-Mar-26
G06 | Aluminum Pergola Work - New Pool Area & BBQ Counter | 24-Mar-26 | 14-May-26
G07 | Aluminum Pergola Work - Villa Front Side | 24-Mar-26 | 14-May-26
G08 | Aluminum Pergola Work - Outside Salon | 24-Mar-26 | 14-May-26
G09 | Supply and Construction of reinforced concrete column to support proposed pergola aluminum tube columns (150mm x 150mm) | 03-Mar-26 | 12-Mar-26
G10 | Construction of BBQ Counter | 12-Mar-26 | 30-Mar-26
G11 | Removal of the exiting pump room & reinstallation of the same pump room new location | 04-Mar-26 | 13-Mar-26
G12 | Supply & construction of wall w/ holes | 10-Mar-26 | 24-Mar-26
H01 | Supply & Installation of new automatic irrigation system | 04-Mar-26 | 12-Mar-26
H02 | Excavation of plant areas: 50cm for shrubs and 1 meter for trees & removal of all garbage with a pickup | 11-Mar-26 | 18-Mar-26
H03 | Supply & Laying of new sweet sand | 17-Mar-26 | 23-Mar-26
H04 | Supply of washingtonia plant 3 meter | 21-Mar-26 | 21-Mar-26
H05 | Supply of traveler plants | 21-Mar-26 | 21-Mar-26
H06 | Supply of oliver tree | 21-Mar-26 | 21-Mar-26
H07 | Supply of Hibiscus plants - Size: 40cm to 50cm | 21-Mar-26 | 21-Mar-26
H08 | Supply of Eranthemum Plant Green | 21-Mar-26 | 21-Mar-26
H09 | Supply of EHaemonculus Plant | 21-Mar-26 | 21-Mar-26
H10 | Supply of Jasmine Murraya Plants - Size: 50cm to 60cm | 21-Mar-26 | 21-Mar-26
H11 | Supply of Canna Lily Plants | 21-Mar-26 | 21-Mar-26
H12 | Supply of Ixora Small Plants | 21-Mar-26 | 21-Mar-26
H13 | Supply of Seasonal Flower | 21-Mar-26 | 21-Mar-26
H14 | Supply of Gravel Stone | 21-Mar-26 | 21-Mar-26
H15 | Plantation Works | 21-Mar-26 | 01-Apr-26

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd'-'mmm'-'yy CurrencyFormat=Dirham